FAST SOCIO

SPRINT PLAN

Aligned to MASTER_PLAN v2.1 — Phase 1 Expanded Scope (with web/PWA pivot, Decision #010)

Sprint length: 1 week. This plan covers Phase 1 (Authentication + Foundation, expanded) in full and previews Phase 2 kickoff. Later phases get detailed sprint breakdowns as each phase begins — see Section 6.

# 1. Current Position

| Field | Value |
| --- | --- |
| Current Phase | Phase 1 — Authentication + Foundation (expanded scope per MASTER_PLAN v2.1) |
| Current Task | Task #003 — Configure Supabase (in progress) |
| Completion | 5% (revised post-pivot — RN scaffold tasks superseded) |
| Active Sprint | Sprint 1 (re-scoped 2026-06-30 to reflect web pivot) |

# 2. Sprint 1 — Foundation & Schema Hardening (re-scoped 2026-06-30)

Goal: finish Supabase config, scaffold the Next.js PWA shell, ship the full hardened schema (including all MASTER_PLAN v2.0 additions), and get RLS + indexing in place before any UI work starts.

| # | Task | Depends On |
| --- | --- | --- |
| 1 | Finish Supabase project configuration (env, keys, @supabase/ssr client setup for Next.js) | — |
| 2 | Create Next.js 15 (App Router) project with TypeScript, Tailwind, ESLint, Prettier (Task 001b) | — |
| 3 | PWA shell: next-pwa or workbox, web manifest with iOS + Android icons, service worker registration, theme-color (Task 001c) | Task 2 |
| 4 | Glass primitives (GlassCard / GlassButton / GlassPill / GlassSheet) and floating glass dock layout (Tasks 001d–001e) | Task 2 |
| 5 | VAPID keypair generation; service worker push handler stub (Task 001f) | Task 3 |
| 6 | Theme provider (dark/light) — next-themes; resolve OQ-10 default (Task 001g) | Task 2 |
| 7 | Migrate core TAD tables (users, profiles, interests, etc.) with FKs + constraints | Task 1 |
| 8 | Add blocked_users table | Task 7 |
| 9 | Add notification_preferences table | Task 7 |
| 10 | Add rate_limit_events table | Task 7 |
| 11 | Add moderation_audit_log table (insert-only, no UPDATE/DELETE policy) | Task 7 |
| 12 | Revise reports table to polymorphic target_type/target_id | Task 7 |
| 13 | Apply indexes from MASTER_PLAN Section 4.7 | Tasks 7–12 |
| 14 | Write and test RLS policies for every table | Tasks 7–12 |
| 15 | Implement aura_score trigger (read-only cache from aura_transactions) | Task 7 |

# 3. Sprint 2 — Auth Flow & Session Management

| # | Task | Depends On |
| --- | --- | --- |
| 1 | Splash / Register / Login / Verify-Pending / Forgot-Password screens in Next.js (auth) route group (UIspec §5.1, gradient bg) | Sprint 1 |
| 2 | OTP/magic-link email verification (Decision #008) — Supabase Auth templates + Next.js server actions | Sprint 1, Task 1 |
| 3 | FAST domain validation (Zod client + Edge Function server) — resolve OQ-9 | Task 1 |
| 4 | Session management — @supabase/ssr cookies + Next.js middleware route guards; refresh-token strategy; multi-device session listing | Sprint 1, Task 1 |
| 5 | Account deletion / data export endpoint (minimal) | Sprint 1, Task 14 |
| 6 | /admin route shell with role-gated middleware (per Decision #010) | Task 4 |
| 7 | Rate-limit Edge Function helper (Task 003e) — used by signup, post-creation, etc. | Sprint 1, Task 10 |

# 4. Sprint 3 — Profile Setup & Phase 1 Exit

| # | Task | Depends On |
| --- | --- | --- |
| 1 | Multi-step profile setup wizard (UIspec §5.2) — photo, dept/semester, interests, bio | Sprint 2 |
| 2 | Avatar upload to Supabase Storage avatars/ bucket with size limits and client-side resize | Task 1 |
| 3 | Profile view + edit screens (UIspec §5.14) | Task 1 |
| 4 | Notification preferences UI hookup (table exists from Sprint 1; UI shipped here for early visibility) | Sprint 1, Task 9 |
| 5 | Phase 1 exit criteria validation: every table has RLS policies tested; Lighthouse PWA install check passes; Supabase reachable; theme toggle works | — |

# 5. Phase 2 Kickoff Preview — Discover

- Migration: likes, passes, message_requests (FKs + composite indexes per Section 4.7).

- Edge Function discover-queue: excludes self/liked/passed/blocked (uses blocked_users); sorts by compatibility (OQ-1 formula).

- Discover UI (UIspec §5.5) — segmented pill tabs, oversized glass card, 3-action row (Pass/Like/Message).

- Card swipe via framer-motion drag gesture. Keyboard fallback ← Pass, → Like, M Message (OQ-13).

- Message request modal (UIspec §5.6) — Next.js parallel route, 100-char cap.

- Rate-limit enforcement on likes/passes/message requests via rate_limit_events.

- Per-feature admin slice: /admin/reports?type=profile.

# 6. Notes

- Sprint 1 was re-scoped on 2026-06-30 to absorb the Next.js scaffold + PWA shell tasks added by Decision #010. The schema-hardening tasks (originally Sprint 1 tasks 2–10) are unchanged.

- Per-feature admin views ship in the corresponding feature phase (e.g. /admin/users in Sprint 3, /admin/reports?type=profile in Phase 2). The separate Phase 11 admin codebase no longer exists.

- Sprint plans for Phases 3–12 will be written at each phase kickoff; the 12-phase structure (Decision #006) is unchanged.